## Sheet1
ACRF Event Planning Guide
Date of Event:
Time of Event:
TASK | PERSON RESPONSIBLE | 6 WEEKS TO GO | 5 WEEKS TO GO | 4 WEEKS TO GO | 3 WEEKS TO GO | 2 WEEKS TO GO | 1 WEEK TO GO | EVENT WEEK | 1 WEEK AFTER
Get Started
Imagine your event | Mary Smith
Register with ACRF | Mary Smith
Build your fundraising page | Mary Smith
Invite guests | Mary Smith
Plan for Success
Plan your event | Mary Smith
Recruit support | Mary/John Smith
Set your Budget | John Smith
Build your Fundraising Page | Mary Smith
Tell the world you're about to outsmart cancer | Mary/John Smith
Create some games for fundraising | Jane Brown
Recuit some volunteer helpers | Jeff Jones
Remind guests: 2 weeks to go | Mary Smith
Remind guests: 1 weeks to go | Mary Smith
Prepare a few words | Mary/John Smith
Confirm guest numbers (RSVPs) | Mary Smith
Confirm food and drinks | Jane Brown
Final check of details, last minute | John Smith
At the Event
Welcome your guests | John Smith
Say a few words | Mary/John Smith
Enjoy your event | Everyone
After the Event
Count the donations | Mary/John Smith
Thank everyone | Mary Smith
Deposit the funds to ACRF | Mary Smith